## Jira_Backlog
Issue ID | Issue Type | Title | Description | Priority | Story Points | Assigned To | Branch Name | Sprint | Status
MLT-0 | Task | create documentation | create SRS , Jira Task Sheet , Presentation , final Report | High | 4 | Simerjeet Kaur | document-setup | Sprint 0 | Done
MLT-1 | Task | Project Setup & Environment Configuration | Initialize Flask project, virtual environment, and Git repository. | High | 8 | Simerjeet Kaur | feature/project-setup | Sprint 1 | To Do
MLT-2 | Task | Integrate NLP Model (en-hi) | Load Helsinki-NLP/opus-mt-en-hi model using HuggingFace Transformers. | High | 13 | Simerjeet Kaur | feature/model-integration | Sprint 1 | To Do
MLT-3 | Task | Create Translation API Endpoint | Develop POST /translate endpoint for handling translation requests. | High | 8 | Simerjeet Kaur | feature/translate-api | Sprint 1 | To Do
MLT-4 | Task | Frontend UI Development | Design responsive UI with input box, language dropdown, and output area. | Medium | 8 | Simerjeet Kaur | feature/frontend-ui | Sprint 2 | To Do
MLT-5 | Task | Connect Frontend with Backend | Implement JavaScript fetch API to connect UI with Flask backend. | Medium | 5 | Simerjeet Kaur | feature/frontend-backend-connection | Sprint 2 | To Do
MLT-6 | Task | Input Validation & Error Handling | Handle empty input, invalid data, and API error responses. | Medium | 3 | Simerjeet Kaur | feature/error-handling | Sprint 2 | To Do
MLT-7 | Task | Performance Optimization | Ensure model loads once at startup and optimize response time. | Medium | 5 | Simerjeet Kaur | feature/performance-optimization | Sprint 2 | To Do
MLT-8 | Task | Multi-Language Expansion Design | Design scalable architecture to support additional language models. | Medium | 8 | Simerjeet Kaur | feature/multilanguage-support | Sprint 3 | To Do
MLT-9 | Task | Render Deployment Configuration | Configure requirements.txt, gunicorn, and deploy on Render. | High | 8 | Simerjeet Kaur | feature/render-deployment | Sprint 3 | To Do
MLT-10 | Task | Testing & Documentation | Perform unit testing and prepare README and project documentation. | Low | 5 | Simerjeet Kaur | feature/testing-documentation | Sprint 3 | To Do